## Phase Summary
CollabHub — Estimated Build Phases
Relative (T-shirt) sizing. Sprint counts assume 2-week sprints. Estimates are indicative and depend on team size and open decisions.
Phase | Focus | Components | Relative size | Est. sprints | Can run in parallel? | Key dependency
Phase 0 | Foundations & shared groundwork | Shared libraries, local dev stack, CI/CD, infrastructure baseline | M | 2 | Precedes all | None (enabling work)
Phase 1 | Identity & access | Identity & access service | M | 3 | No — blocks others | Phase 0
Phase 2 | Core services (parallel) | Team chat, Collaborative design, Files & storage | L | 5 | Yes — 3 tracks in parallel | Phase 1
Phase 3 | Background processing | Background worker (indexing, thumbnails, notifications, retention) | L | 3 | Partly — can start once jobs exist | Phase 2 (partial)
Phase 4 | Web application | React/TypeScript single-page app | L | 5 | No — needs stable back-end | Phases 1–3
Phase 5 | Hardening & first release | Testing, performance, security, deployment, polish | M | 2 | No — final | Phases 1–4
Indicative total | Calendar view — parallelism means elapsed time is less than the sum |  |  | 20
Sum of sprints (all work): |  |  |  | 20
Estimated elapsed sprints (with parallelism): |  |  |  | 17
Note: Phase 3 (background processing) overlaps the core services and web-app phases, so it is excluded from the elapsed figure.

## Component Detail
CollabHub — Component Estimates
Per-component relative sizing and rationale. Sizes: S small, M medium, L large.
Phase | Component | Relative size | Est. sprints | What it delivers | Main complexity / risk | Depends on
Phase 0 | Shared libraries & platform groundwork | M | 2 | Common security, error handling, monitoring, job plumbing; local dev environment; build & deploy pipeline | Getting shared conventions right early pays off later; low external risk | None
Phase 1 | Identity & access service | M | 3 | Sign-in, security tokens, workspace membership and roles, identity federation | External identity (OIDC/SAML) integration is high-touch; enterprise SSO can be deferred | Phase 0
Phase 2 | Team chat service | L | 4 | Channels, messages, threads, reactions, read receipts, real-time delivery | Real-time coordination across multiple servers; pagination and read-receipt edge cases | Phase 1
Phase 2 | Collaborative design service | L | 5 | Live shared design documents, sync between editors, safe saving of state, presence | Live-sync protocol and reliable save/recovery; a core open decision | Phase 1
Phase 2 | Files & storage service | M | 3 | Upload/download of images and attachments, efficient file storage, thumbnails | Secure direct-to-storage uploads; virus-scanning is an open decision | Phase 1
Phase 3 | Background worker | L | 3 | Search indexing, image thumbnails, notifications, design exports, housekeeping | Reliable retry/recovery; design-export engine is involved and may be deferred | Phase 2 (partial)
Phase 4 | Web application | L | 5 | The single user-facing app: chat + design UI, live presence, uploads, sign-in | Complex real-time state; sign-in flow; design rendering performance | Phases 1–3
Phase 5 | Hardening & first release | M | 2 | End-to-end testing, performance tuning, security review, deployment, polish | Ensuring quality across all blocks before launch | Phases 1–4
Total (all component effort) |  |  | 27

## Legend & Assumptions
Sizing Legend & Assumptions
T-shirt size | Meaning | Rough effort
S | Small — well-understood, low risk | ~1–2 sprints
M | Medium — moderate scope or some unknowns | ~2–3 sprints
L | Large — broad scope, real-time or complex logic | ~3–5 sprints
XL | Extra large — would normally be split into smaller pieces | 5+ sprints
Assumptions
• | Sprints are 2 weeks long.
• | Sizes are relative and indicative, not a committed schedule or budget.
• | Phase 2 (team chat, collaborative design, files) assumes three tracks worked in parallel by separate people or squads.
• | Phase 3 (background processing) can begin once the core services start producing work, so it overlaps Phases 2 and 4.
• | Enterprise single sign-on (SAML), design exports, and native mobile are treated as deferrable beyond the first release.
• | The web application is scheduled last because it depends on stable back-end features.
• | Estimates will firm up as the open decisions in the design's decisions register are resolved.